## User Stories Backlog
USER STORIES & PRODUCT BACKLOG
Agile Backlog for D365 BC Implementation
Story ID | Epic | User Story | Acceptance Criteria | Story Points | Priority | Sprint | Status | Assigned To
US-001 | Multi-Channel Orders | As a Sales Manager, I want to view all orders from retail, e-commerce, and B2B channels in one screen, so that I can monitor total sales holistically | 1. User can filter orders by channel 2. All channels display in unified grid 3. Order details accessible from grid 4. Export to Excel available | 5 | High | Sprint 3 | Done | Dev Team
US-002 | Inventory Transfer | As a Warehouse Manager, I want to initiate stock transfers between locations, so that I can rebalance inventory based on demand | 1. User can create transfer order 2. System validates available quantity 3. Transfer updates both locations 4. Audit trail created 5. Email notification sent | 8 | High | Sprint 4 | Done | Dev Team
US-003 | Shopify Sync | As an E-commerce Manager, I want Shopify orders to automatically sync to D365 BC, so that I don't have to manually enter orders | 1. Order appears in D365 BC within 2 min 2. Customer auto-created if new 3. Inventory reserved automatically 4. Sync errors logged | 13 | Critical | Sprint 5 | In Progress | Integration Team
US-004 | Credit Limit | As a Finance Manager, I want the system to block orders exceeding customer credit limits, so that we minimize bad debt | 1. Warning displayed when limit exceeded 2. Cannot post without approval 3. Approval workflow triggers 4. Credit limit history tracked | 5 | High | Sprint 6 | Backlog | Dev Team