## Test Summary
USER ACCEPTANCE TEST PLAN
Microsoft Dynamics 365 Business Central
TechGear Distribution Pte Ltd
TEST EXECUTION SUMMARY
Metric | Count
Total Test Cases | 127
Passed | 121
Failed | 3
Blocked | 2
Not Executed | 1
Pass Rate | 95.3%
Test Coverage by Module
Financial Management | 35 test cases
Sales & Service | 28 test cases
Purchasing | 18 test cases
Inventory & Warehouse | 22 test cases
Integrations | 16 test cases
Reporting | 8 test cases

## Finance Test Cases
TC ID | Test Scenario | Module | Priority | Preconditions | Test Steps | Expected Result | Actual Result | Status | Tester | Date | Defect ID
TC-FIN-001 | Create sales invoice in USD with exchange rate | Finance | Critical | Customer exists; USD exchange rate configured | 1. Go to Sales Invoices 2. Create new invoice 3. Select customer (USD) 4. Add line item 5. Post invoice 6. Verify GL entries | Invoice posted; GL entries created with correct SGD equivalent using daily exchange rate | As expected | Pass | David Tan | 2025-05-15
TC-FIN-002 | Automated bank reconciliation with MT940 file | Finance | High | Bank account setup; MT940 file available from DBS bank | 1. Import bank statement (MT940) 2. Run auto-match 3. Review matches 4. Post reconciliation 5. Verify bank account balance | Transactions auto-matched (>90%); bank account reconciled; GL updated | As expected | Pass | Sarah Lim | 2025-05-16
TC-FIN-003 | Intercompany transaction between SG and MY entities | Finance | Critical | Both entities configured; IC partner setup complete | 1. Create IC sales order in SG entity 2. Post transaction 3. Switch to MY entity 4. Verify IC purchase order created 5. Post IC purchase 6. Run IC elimination report | IC transaction flows between entities; elimination entries auto-generated for consolidation | Failed - IC partner not found | Fail | Michael Chen | 2025-05-17 | DEF-012
TC-FIN-004 | Fixed asset depreciation calculation (straight-line) | Finance | High | Fixed asset registered; depreciation book configured | 1. Register new laptop (cost: $2,000) 2. Set useful life: 3 years 3. Set depreciation method: Straight-line 4. Run monthly depreciation batch job 5. Review FA ledger entries | Monthly depreciation = $55.56 ($2,000 / 36 months); GL entries posted correctly | As expected | Pass | David Tan | 2025-05-18
TC-FIN-005 | Malaysia SST calculation on sales invoice | Finance | Critical | SST module enabled; Tax codes configured (6% SST) | 1. Create sales invoice for MY customer 2. Select taxable item 3. Verify SST auto-calculated 4. Post invoice 5. Run SST-02 report | SST calculated at 6%; Tax amount = $600 on $10,000 sale; SST-02 report shows transaction | As expected | Pass | Jessica Wong | 2025-05-19
TC-FIN-006 | Multi-dimensional reporting (Dept + Cost Center) | Finance | Medium | Dimensions configured; Default dimension rules set | 1. Post invoice with Department = Sales, Cost Center = Retail SG 2. Run P&L by Dimension report 3. Verify amounts allocated correctly | Transaction appears in Sales dept, Retail SG cost center; P&L balances match GL | As expected | Pass | Sarah Lim | 2025-05-20
TC-FIN-007 | Month-end close process (consolidated) | Finance | Critical | All transactions posted for the month; IC transactions complete | 1. Run month-end checklist 2. Review open transactions 3. Post accruals/deferrals 4. Run consolidation 5. Generate consolidated financial statements | Month-end close completed in <2 days; Consolidated P&L and Balance Sheet accurate | As expected (1.8 days) | Pass | David Tan | 2025-05-22

## Sales Test Cases
TC ID | Test Scenario | Module | Priority | Preconditions | Test Steps | Expected Result | Actual Result | Status | Tester | Date | Defect ID
TC-SAL-001 | Create retail sales order from POS | Sales | Critical | LS Retail POS configured; Integration active | 1. Create sale in POS (item: Laptop, qty: 1, price: $1,500) 2. Complete payment 3. Verify order syncs to D365 BC 4. Check inventory reduction | Sales order created in D365 BC; Inventory reduced by 1 unit; Revenue posted to GL | As expected | Pass | Store Manager | 2025-05-20
TC-SAL-002 | E-commerce order sync from Shopify | Sales | Critical | Shopify integration configured; Test order in Shopify | 1. Place order on Shopify website 2. Wait for sync (real-time) 3. Verify order in D365 BC 4. Check customer record created | Order appears in D365 BC within 2 minutes; Customer auto-created; Inventory reserved | As expected (87 seconds) | Pass | Michael Chen | 2025-05-21
TC-SAL-003 | Three-tier pricing (VIP customer gets discount) | Sales | High | Customer assigned to VIP price group; VIP prices configured | 1. Create sales order for VIP customer 2. Add item (standard retail: $100) 3. Verify VIP price applied 4. Post order | VIP price auto-applied ($80 = 20% discount); Order total correct | As expected | Pass | Sarah Lim | 2025-05-22
TC-SAL-004 | Credit limit check (order exceeds limit) | Sales | High | Customer credit limit = $10,000; Current balance = $8,000 | 1. Create sales order value = $5,000 2. Attempt to post 3. Review warning message | System blocks posting with error: "Order exceeds customer credit limit"; Cannot proceed | Failed - no warning shown | Fail | David Tan | 2025-05-23 | DEF-015
TC-SAL-005 | Sales return and refund processing | Sales | Medium | Original sales invoice posted; Return authorization enabled | 1. Create sales return order (ref original invoice) 2. Add return line (defective item) 3. Post return 4. Process refund 5. Verify inventory restocked | Return posted; Credit memo issued; Inventory quantity increased; Refund payment created | As expected | Pass | Jessica Wong | 2025-05-24

## Integration Test Cases
TC ID | Test Scenario | Module | Priority | Preconditions | Test Steps | Expected Result | Actual Result | Status | Tester | Date | Defect ID
TC-INT-001 | Shopify inventory sync (15-min batch) | Integration | Critical | D365 BC has inventory data; Shopify connected | 1. Update stock in D365 BC (reduce qty by 10) 2. Wait 15 minutes for batch job 3. Check Shopify inventory level 4. Verify sync log | Shopify inventory updated within 15 minutes; Sync log shows success; No errors | As expected (12 min) | Pass | Michael Chen | 2025-05-25
TC-INT-002 | Payment gateway webhook (successful payment) | Integration | High | Payment gateway configured; Test card available | 1. Create e-commerce order 2. Process payment via gateway 3. Verify webhook received 4. Check payment posted in D365 BC | Webhook received within 5 seconds; Payment auto-posted; Invoice marked as paid | Blocked - webhook endpoint unreachable | Blocked | Sarah Lim | 2025-05-26 | DEF-018
TC-INT-003 | Power BI dashboard data refresh | Integration | Medium | Power BI workspace configured; Dashboards published | 1. Post new sales transactions in D365 BC 2. Trigger Power BI refresh 3. Verify dashboard updates 4. Check data freshness timestamp | Dashboard data refreshed; Sales KPIs reflect new transactions; Timestamp updated | As expected | Pass | David Tan | 2025-05-27

## Defect Log
DEFECT TRACKING LOG
Defect ID | Related TC | Severity | Description | Steps to Reproduce | Assigned To | Status | Resolution | Closed Date
DEF-012 | TC-FIN-003 | High | IC partner not found during transaction posting | Create IC sales order; select MY partner; attempt to post | Microsoft Partner | Fixed | IC partner master data was missing in MY entity. Added partner and retested successfully. | 2025-05-18
DEF-015 | TC-SAL-004 | Medium | Credit limit check not triggering warning | Create sales order exceeding credit limit; try to post | Microsoft Partner | Fixed | Credit limit check was disabled in customer posting group. Re-enabled and tested. | 2025-05-24
DEF-018 | TC-INT-002 | High | Payment webhook endpoint unreachable (404 error) | Process payment in gateway; webhook fails to reach D365 BC | Integration Dev | In Progress | Investigating firewall rules; endpoint URL may need to be whitelisted.