## Stakeholder Register
STAKEHOLDER REGISTER
D365 Business Central Implementation - TechGear Distribution
Name | Role/Title | Department | Power | Interest | Classification | Influence Strategy | Communication Frequency
Jessica Wong | CEO | Executive | High | High | Manage Closely | Monthly steering committee; approve all major decisions | Monthly + Ad-hoc
David Tan | CFO | Finance | High | High | Manage Closely | Weekly project updates; sign-off on financial requirements | Weekly
Sarah Lim | Operations Director | Operations | High | High | Manage Closely | Bi-weekly process reviews; UAT lead for warehouse/retail | Bi-weekly
Michael Chen | IT Manager | IT | Medium | High | Keep Informed | Technical design reviews; infrastructure readiness | Weekly
Rachel Ng | Finance Manager | Finance | Medium | High | Keep Informed | Requirements workshops; UAT execution for finance module | Bi-weekly
Ahmad Hassan | Warehouse Manager (MY) | Operations | Low | High | Keep Informed | Training sessions; feedback on warehouse processes | Monthly
Store Managers (3) | Retail Store Managers | Retail | Low | High | Keep Informed | Training delivery; POS integration feedback | Monthly
James Koh | E-commerce Manager | Sales | Medium | High | Keep Informed | Shopify integration requirements and testing | Bi-weekly
Linda Tan | Accounts Payable Clerk | Finance | Low | Medium | Monitor | End-user training; process feedback | Monthly
IT Support Team (2) | IT Support Specialists | IT | Low | Medium | Monitor | Technical training; L1 support preparation | Monthly
Microsoft Partner | Implementation Partner | External | High | High | Manage Closely | Daily standups; technical architecture oversight | Daily
Board of Directors | Board Members | Governance | High | Low | Keep Satisfied | Quarterly business case updates; ROI reporting | Quarterly

## RACI Matrix
RACI MATRIX - PROJECT ACTIVITIES
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Activity | Project Manager | Lead BA | CFO | Ops Director | IT Manager | MS Partner | End Users
Project Charter Development | A | R | C | C | I | C | I
Requirements Elicitation | I | A | C | C | C | I | C
Business Requirements Document | C | A/R | A | C | C | I | I
Gap Analysis | C | R | C | C | I | A | I
Solution Design | C | C | I | I | C | A/R | I
Configuration & Customization | I | C | I | I | C | A/R | I
Data Migration Strategy | C | R | A | C | C | C | I
Data Cleansing & Mapping | I | C | C | R | R | C | I
Integration Development | C | C | I | I | C | A/R | I
UAT Planning | C | A/R | C | C | C | I | I
UAT Execution | I | C | R | R | R | C | R
Defect Management | C | R | I | I | C | A | I
Training Material Development | C | R | I | C | C | C | I
End User Training Delivery | C | R | I | A | C | C | C
Go-Live Cutover | A | C | I | C | R | R | I
Post-Go-Live Support (Week 1) | C | R | I | C | R | A | C
Change Requests | A | R | C | C | C | C | I
Lessons Learned | A | R | C | C | C | C | C

## Communication Plan
PROJECT COMMUNICATION PLAN
Communication Type | Purpose | Audience | Owner | Frequency | Method | Template/Format
Project Status Report | Track milestones, risks, issues | Steering Committee | Project Manager | Weekly | Email + Dashboard | PowerPoint deck
Steering Committee Meeting | Decision-making, escalations | C-level executives | Project Sponsor | Monthly | In-person/Teams | Meeting agenda
Working Team Standup | Daily coordination | Core project team | Scrum Master | Daily | Teams call | Kanban board
Requirements Workshop | Gather detailed requirements | SMEs, End Users | Lead BA | As needed | In-person workshop | Workshop template
UAT Status Meeting | Review test progress, defects | UAT team, BA, Partner | Lead BA | Daily (during UAT) | Teams call | Test dashboard
Change Control Board | Approve/reject change requests | PM, BA, CFO, Partner | Project Manager | Bi-weekly | Teams meeting | Change request form
Training Sessions | Prepare end users for go-live | All system users | Lead BA | 2 weeks pre-launch | In-person/Teams | Training materials
Town Hall Update | Broad project updates | All employees | Project Sponsor | Quarterly | Company meeting | Presentation

## Power-Interest Grid
STAKEHOLDER POWER/INTEREST GRID
| Manage Closely (High Power, High Interest) Jessica Wong (CEO) David Tan (CFO) Sarah Lim (Ops Dir) MS Partner |  | Keep Satisfied (High Power, Low Interest) Board of Directors
POWER
| Keep Informed (Low Power, High Interest) Michael Chen (IT Mgr) Rachel Ng (Fin Mgr) James Koh (E-comm) Store Managers |  | Monitor (Low Power, Low Interest) AP Clerk IT Support Team
INTEREST